## Project plan
Phase | Steps | Week | Task | Group member | Progress
1 | 1 | 1 | Group formed | All | completed
| 2 | 1 | Select the topic | All | completed
| 3 | 1 | Roles assignment | All | completed
| 4 | 2 | Develop project plan (WBS) for the data warehouse project | Irina Becknell | completed
| 5 | 2 | Inform professor of the project topic and submit group work schedule to professor | Irina Becknell
| 6 | 3 to 12 | Inform professor of the project progress and clarify any questions with professor | Irina Becknell
| 7 | 4 | Writing of the Abstract of the project report | Irina Becknell
| 8 | 4 | Writing of the Introduction of the project report | Irina Becknell
2 | 9 | 4 | Data Model/DDL design (DB schema consisting of one FACT table and four DIMENSION tables). Record and include DDL script design for Appendix | Brandon Russell
| 10 | 4 | Requirements analysis (develop description of the data sources, analyze the requirements documented in the introduction.) | Thomas Jensen
| 11 | 4 | ETLs/DMLs (identification of the data sources, data map, and the methodology used to load the data. Identify, describe and record the DML or SQL*Loader scripts for Appendix ) | Chan, Joe
| 12 | 6 | Data Model/DDL development and implementation. Record steps for the body of the report | Brandon Russell
| 13 | 7 | Writing SQL queries. Record the scripts for the Appendix | Brandon Russell
| 14 | 8 | Report analysis (development of all the report scenarios (at least 4) that demonstrate how the requirements identified in the introduction were met. Identify and record the SQL scripts in the Appendix). | Thomas Jensen
3 | 15 | 10 | Writing of Lesson learned section (record any problems and issues) | Irina Becknell
| 16 | 10 | Writing of Conclusion of the project report (one page discussion of the project, explain how has this report solved the business needs identified in the Introduction.) | Irina Becknell
| 17 | 11 | Review of the project report, make necessary changes. Submission of the project | All

## Team members and roles
Group 3, DBST 665
Team Member | Role
Becknell, Irina | Project Lead
Chan, Joe | Business Analyst
Jensen, Thomas | Database Administrator (DBA)
Russell, Brandon | Database Developer